## Sheet1
Project: holy-cheese Server: dev.azure.com/techwavellc Query: Holy Cheese Import List type: Tree
ID | Work Item Type | Title 1 | Title 2 | Title 3 | Title 4 | Title 5 | Assigned To | State | Effort | Area Path | Iteration Path | Priority | Story Points | Description | Acceptance Criteria
1 | Epic | Project setup |  |  |  |  | Edward Fry | Active | 5 | \admin\project-management | \mvp\2025-sprint1 | 1 |  | Set up the work tools necessary for everyone to collaborate on the project
2 | Feature |  | Set up source control |  |  |  | Edward Fry | Resolved | 2 | \admin\devops | \mvp\2025-sprint1 | 2 |  | Identify and set up source control for the project
3 | Feature |  | Set up game development tool |  |  |  | Edward Fry | Active |  | \admin\devops | \mvp\2025-sprint1 | 2 |  | Identify and set up the game development engine and environment. Choose from Unity, Unreal, or Godot.
5 | Feature |  | Set up team collaboration tools |  |  |  | Edward Fry | Active | 2 | \admin\it | \mvp\2025-sprint1 | 2 |  | Configure and integrate tools that will facilitate easy collaboration between the members of the team.
4 | Feature |  | Set up work tracking system |  |  |  | Edward Fry | Active | 3 | \admin\project-management | \mvp\2025-sprint1 | 2 |  | Set up the work tracking system and configure high level work items to begin the project.
6 | Epic | Create the animations for the sprites | [5 empty] | New |  | \assets\animations | \mvp | 2 |  | Create sprite sheets for each of the tower and enemy types in the game
10 | Feature |  | Draw the sprite sheets for the rat units |  |  |  |  | New |  | \assets\animations | \mvp | 2
7 | Feature |  | Concept art for the cat towers |  |  |  |  | New |  | \assets\graphics | \mvp | 2
8 | Feature |  | Concept art for the rat units |  |  |  | Heather Fry | New |  | \assets\graphics | \mvp | 2
9 | Feature |  |  | Draw the sprite sheets for cat towers |  |  |  | New |  | \assets\animations | \mvp | 2
11 | User Story |  |  |  | Create the sprite sheet for claw tower |  | Heather Fry | Active |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the cat claw tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #7
12 | Task |  |  |  |  | Claw Tower ¦ Sketch | Heather Fry | Closed |  | \assets\animations | \mvp\2025-sprint1 | 2 |  | Draw the sketch for the claw tower. The tower will swipe by .....
14 | Task |  |  |  |  | Claw Tower ¦ Coloring | Heather Fry | Active |  | \assets\animations | \mvp\2025-sprint1 | 2
16 | Epic | Game rules |  |  |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 2
17 | Feature |  | Video game design document |  |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 2
19 | User Story |  |  | Write game design stories |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 1 |  | We need to know who the target audience is for the game design. Instinctively, this will be the people creating and testing the game, so we need to define that further to know exactly the kinds of information that they will need in order to do their work. | Identify who will need to use the design documentation and what they need to get out of them. Write user stories for those users.
20 | User Story |  |  | Define the basic game structure |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 2 |  | As a developer, I need to know the basic rules of the game so that I can write the code to implement those rules. Video Game Document.docx - Repos | * What kind of game will it be? Tower defense * What is the goal of the game? Stop invading rats from getting through a maze that is defended by towers of cats * How do the towers stop the invaders specifically? <Math> * How is balance maintained? * Do the towers "level up"? How so? * Do the enemies "level up"? How? * What is the minimum viable product (MVP)? Answer these questions in detail in a game design document.
18 | Feature |  | Storyboarding documentation |  |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 2
21 | User Story |  |  | Intro |  |  | lindamf | Resolved |  | \game-design\rules | \mvp\2025-sprint1 | 2
22 | User Story |  |  | Level 1 |  |  | lindamf | Resolved |  | \game-design\rules | \mvp\2025-sprint1 | 2
23 | User Story |  |  | Level 2 |  |  | lindamf | Resolved |  | \game-design\rules | \mvp\2025-sprint1 | 2
24 | User Story |  |  | Level 3 |  |  | lindamf | Active |  | \game-design\rules | \mvp\2025-sprint1 | 3
53 | Epic | Project management |  |  |  |  | Edward Fry | New | 8 | \admin\project-management | \mvp | 2
54 | Feature |  | Tools |  |  |  | Edward Fry | New | 5 | \admin\project-management | \mvp | 2 |  | Set up the work tools necessary for everyone to collaborate on the project
55 | User Story |  |  | Source control - Git, GitKraken, Azure Devops |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2 | Identify and set up source control for the project
56 | User Story |  |  | Game engine - Godot |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2 | Identify and set up the game development engine and environment. Choose from Unity, Unreal, or Godot.
57 | User Story |  |  | Team collaboration - Teams |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2 | Configure and integrate tools that will facilitate easy collaboration between the members of the team.
58 | User Story |  |  | Work tracking - Azure Devops (azdo) |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2 | Set up the work tracking system and configure high level work items to begin the project.
59 | Feature |  | Work breakdown |  |  |  | Edward Fry | New | 3 | \admin\project-management | \mvp | 1
60 | User Story |  |  | Basic work outline for entire project |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 1 | 2
61 | User Story |  |  | Enter work item outline into azdo |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2
62 | Feature |  | Schedule |  |  |  | Edward Fry | New | 2 | \admin\project-management | \mvp | 2
63 | User Story |  |  | Build DAG from the WBS |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2
64 | User Story |  |  | Set the project milestones |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2
65 | User Story |  |  | Determine target release dates |  |  | Edward Fry | New |  | \admin\project-management | \mvp\2025-sprint1 | 2 | 2
66 | Epic | Concept development |  |  |  |  | lindamf | New | 13 | \game-design | \mvp | 3
67 | Feature |  | Training |  |  |  | Edward Fry | New | 3 | \game-design | \mvp\2025-sprint1 | 2
68 | Research |  |  | Using the project tools training |  |  | Edward Fry | New | 1 | \game-design | \mvp\2025-sprint1 | 2
69 | Research |  |  | Writing a user story training |  |  | Edward Fry | New | 1 | \game-design | \mvp | 2
70 | Feature |  | Core mechanics |  |  |  | lindamf | New | 2 | \game-design\rules | \mvp\2025-sprint1 | 1
71 | Research |  |  | Research how these should work |  |  | lindamf | New | 1 | \game-design\rules | \mvp\2025-sprint1 | 1
72 | User Story |  |  | Adapt theory to holy cheese |  |  | lindamf | New |  | \game-design\rules | \mvp\2025-sprint1 | 1 | 2
73 | User Story |  |  | Resource management |  |  | lindamf | New |  | \game-design\rules | \mvp | 1 | 2
74 | Feature |  | Gameplay loop |  |  |  | lindamf | New | 2 | \game-design\rules | \mvp | 1
75 | Research |  |  | Research gameplay loops |  |  | lindamf | New | 1 | \game-design\rules | \mvp | 1
76 | User Story |  |  | Describe the holy cheese play loop(s) unambiguously |  |  | lindamf | New |  | \game-design\rules | \mvp | 1 | 2
77 | Feature |  | Level structure and mechanics |  |  |  | lindamf | New | 2 | \game-design\levels | \mvp | 1
78 | Research |  |  | Research level design for tower defense games |  |  | lindamf | New | 1 | \game-design\levels | \mvp | 1
79 | User Story |  |  | Enumerate the Holy Cheese level design principles |  |  | lindamf | New |  | \game-design\levels | \mvp | 1 | 2
80 | Feature |  | Prototyping |  |  |  | Elizabeth Fry | New | 5 | \game-design | \mvp | 2
81 | Spike |  |  | Build basic game prototype |  |  | Elizabeth Fry | New | 3 | \game-design | \mvp | 2
82 | Task |  |  |  | New project in Godot for game |  | Elizabeth Fry | New |  | \game-design | \mvp | 2
83 | Task |  |  |  | Simplistic level and units |  | Elizabeth Fry | New |  | \game-design | \mvp | 2
84 | Task |  |  |  | Basic mechanics |  | Elizabeth Fry | New |  | \game-design | \mvp | 2
85 | Task |  |  |  | Telemetry for mechanics |  | Elizabeth Fry | New |  | \game-design | \mvp | 2
86 | Task |  |  |  | Iterate on mechanics |  | Elizabeth Fry | New |  | \game-design | \mvp | 2
87 | Spike |  |  | Early art and animation |  |  | Heather Fry | New | 3 | \game-design | \mvp | 2
88 | Task |  |  |  | Basic cat tower animation |  | Heather Fry | New |  | \game-design | \mvp | 2
89 | Task |  |  |  | Basic rat unit animation |  | Heather Fry | New |  | \game-design | \mvp | 2
90 | Task |  |  |  | Basic level image |  | Heather Fry | New |  | \game-design | \mvp | 2
91 | Feature |  | Progression systems |  |  |  | lindamf | New | 8 | \game-design\rules | \mvp | 2
92 | User Story |  |  | Unit base mechanics |  |  | lindamf | New |  | \game-design\rules | \mvp | 2 | 3
93 | Task |  |  |  | Hero mechanics - General Clawdius Maximus |  | lindamf | New |  | \game-design\rules | \mvp | 2
94 | Task |  |  |  | Hero mechanics - Sir Pounce-a-Lot |  | lindamf | New |  | \game-design\rules | \mvp | 2
95 | Task |  |  |  | Hero mechanics - Meowdusa |  | lindamf | New |  | \game-design\rules | \mvp | 2
96 | Task |  |  |  | Hero mechanics - Purrlin the Mage |  | lindamf | New |  | \game-design\rules | \mvp | 2
97 | Task |  |  |  | Hero mechanics - Graybeard the Gnawer |  | lindamf | New |  | \game-design\rules | \mvp | 2
98 | Task |  |  |  | Hero mechanics - Fleablight |  | lindamf | New |  | \game-design\rules | \mvp | 2
99 | Task |  |  |  | Hero mechanics - Stormtail |  | lindamf | New |  | \game-design\rules | \mvp | 2
100 | Task |  |  |  | Hero mechanics - Chitterjaw |  | lindamf | New |  | \game-design\rules | \mvp | 2
101 | Task |  |  |  | Hero mechanics - Rat King |  | lindamf | New |  | \game-design\rules | \mvp | 2
102 | Task |  |  |  | Basic Squeakers |  | lindamf | New |  | \game-design\rules | \mvp | 2
103 | Task |  |  |  | Flashpaws |  | lindamf | New |  | \game-design\rules | \mvp | 2
104 | Task |  |  |  | Mindwhiskers |  | lindamf | New |  | \game-design\rules | \mvp | 2
105 | Task |  |  |  | Titantails |  | lindamf | New |  | \game-design\rules | \mvp | 2
106 | Task |  |  |  | Voltfangs |  | lindamf | New |  | \game-design\rules | \mvp | 2
107 | Task |  |  |  | Shadowsnouts |  | lindamf | New |  | \game-design\rules | \mvp | 2
108 | Task |  |  |  | Gutrotters |  | lindamf | New |  | \game-design\rules | \mvp | 2
109 | Task |  |  |  | Bonecrunchers |  | lindamf | New |  | \game-design\rules | \mvp | 2
110 | Task |  |  |  | Shriekmaw |  | lindamf | New |  | \game-design\rules | \mvp | 2
111 | Task |  |  |  | Cinderfur |  | lindamf | New |  | \game-design\rules | \mvp | 2
112 | Task |  |  |  | Frostfeet |  | lindamf | New |  | \game-design\rules | \mvp | 2
113 | Task |  |  |  | Fleabombs |  | lindamf | New |  | \game-design\rules | \mvp | 2
114 | Task |  |  |  | Chewtank |  | lindamf | New |  | \game-design\rules | \mvp | 2
115 | Task |  |  |  | Basic Claw Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
116 | Task |  |  |  | Sticky Paws Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
117 | Task |  |  |  | Cat Nap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
118 | Task |  |  |  | Pied Piper Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
119 | Task |  |  |  | Yarn Ball Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
120 | Task |  |  |  | Hero Towers |  | lindamf | New |  | \game-design\rules | \mvp | 2
121 | Task |  |  |  | Mouse Trap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
122 | Task |  |  |  | Sticky Trap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
123 | Task |  |  |  | Fish Bone Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
124 | Task |  |  |  | Tuna Storm Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
125 | Task |  |  |  | Drenched Paw Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
126 | Task |  |  |  | Blazing Whisker Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
127 | User Story |  |  | Difficulty mechanics |  |  | lindamf | New |  | \game-design\rules | \mvp | 2 | 2
128 | Task |  |  |  | Easy mechanics |  | lindamf | New |  | \game-design\rules | \mvp | 2
129 | Task |  |  |  | Medium mechanics |  | lindamf | New |  | \game-design\rules | \mvp | 2
130 | Task |  |  |  | Hard mechanics |  | lindamf | New |  | \game-design\rules | \mvp | 2
131 | User Story |  |  | Unit progressions |  |  | lindamf | New |  | \game-design\rules | \mvp | 2 | 5
132 | Task |  |  |  | Hero mechanics - General Clawdius Maximus |  | lindamf | New |  | \game-design\rules | \mvp | 2
133 | Task |  |  |  | Hero mechanics - Sir Pounce-a-Lot |  | lindamf | New |  | \game-design\rules | \mvp | 2
134 | Task |  |  |  | Hero mechanics - Meowdusa |  | lindamf | New |  | \game-design\rules | \mvp | 2
135 | Task |  |  |  | Hero mechanics - Purrlin the Mage |  | lindamf | New |  | \game-design\rules | \mvp | 2
136 | Task |  |  |  | Hero mechanics - Graybeard the Gnawer |  | lindamf | New |  | \game-design\rules | \mvp | 2
137 | Task |  |  |  | Hero mechanics - Fleablight |  | lindamf | New |  | \game-design\rules | \mvp | 2
138 | Task |  |  |  | Hero mechanics - Stormtail |  | lindamf | New |  | \game-design\rules | \mvp | 2
139 | Task |  |  |  | Hero mechanics - Chitterjaw |  | lindamf | New |  | \game-design\rules | \mvp | 2
140 | Task |  |  |  | Hero mechanics - Rat King |  | lindamf | New |  | \game-design\rules | \mvp | 2
141 | Task |  |  |  | Basic Squeakers |  | lindamf | New |  | \game-design\rules | \mvp | 2
142 | Task |  |  |  | Flashpaws |  | lindamf | New |  | \game-design\rules | \mvp | 2
143 | Task |  |  |  | Mindwhiskers |  | lindamf | New |  | \game-design\rules | \mvp | 2
144 | Task |  |  |  | Titantails |  | lindamf | New |  | \game-design\rules | \mvp | 2
145 | Task |  |  |  | Voltfangs |  | lindamf | New |  | \game-design\rules | \mvp | 2
146 | Task |  |  |  | Shadowsnouts |  | lindamf | New |  | \game-design\rules | \mvp | 2
147 | Task |  |  |  | Gutrotters |  | lindamf | New |  | \game-design\rules | \mvp | 2
148 | Task |  |  |  | Bonecrunchers |  | lindamf | New |  | \game-design\rules | \mvp | 2
149 | Task |  |  |  | Shriekmaw |  | lindamf | New |  | \game-design\rules | \mvp | 2
150 | Task |  |  |  | Cinderfur |  | lindamf | New |  | \game-design\rules | \mvp | 2
151 | Task |  |  |  | Frostfeet |  | lindamf | New |  | \game-design\rules | \mvp | 2
152 | Task |  |  |  | Fleabombs |  | lindamf | New |  | \game-design\rules | \mvp | 2
153 | Task |  |  |  | Chewtank |  | lindamf | New |  | \game-design\rules | \mvp | 2
154 | Task |  |  |  | Basic Claw Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
155 | Task |  |  |  | Sticky Paws Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
156 | Task |  |  |  | Cat Nap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
157 | Task |  |  |  | Pied Piper Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
158 | Task |  |  |  | Yarn Ball Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
159 | Task |  |  |  | Hero Towers |  | lindamf | New |  | \game-design\rules | \mvp | 2
160 | Task |  |  |  | Mouse Trap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
161 | Task |  |  |  | Sticky Trap Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
162 | Task |  |  |  | Fish Bone Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
163 | Task |  |  |  | Tuna Storm Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
164 | Task |  |  |  | Drenched Paw Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
165 | Task |  |  |  | Blazing Whisker Tower |  | lindamf | New |  | \game-design\rules | \mvp | 2
166 | User Story |  |  | Player progression |  |  | lindamf | New |  | \game-design\rules | \mvp | 2 | 2
167 | Task |  |  |  | Design player progression system |  | lindamf | New |  | \game-design\rules | \mvp | 2
168 | Task |  |  |  | Document player progression system |  | lindamf | New |  | \game-design\rules | \mvp | 2
169 | Spike |  |  | Identify other desired progressions |  |  | lindamf | New | 1 | \game-design\rules | \mvp | 3
170 | Task |  |  |  | Study other tower games for progression ideas |  | lindamf | New |  | \game-design\rules | \mvp | 3
171 | Task |  |  |  | Brainstorm progression with the team |  | lindamf | New |  | \game-design\rules | \mvp | 3
172 | Task |  |  |  | Document additonal progression systems |  | lindamf | New |  | \game-design\rules | \mvp | 3
173 | Epic | Story development |  |  |  |  | lindamf | New | 8 | \game-design\story | \mvp | 3
174 | Feature |  | Story outline |  |  |  | lindamf | New | 2 | \game-design\story | \mvp | 3
175 | User Story |  |  | Narrative guidelines |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 2
176 | User Story |  |  | Character sheets |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 2
177 | User Story |  |  | Story outline |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 2
178 | User Story |  |  | Identify story cutscenes |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
179 | Feature |  | Storyboard the cutscenes |  |  |  | lindamf | New | 5 | \game-design\story | \mvp | 3
180 | User Story |  |  | Introduction |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
181 | User Story |  |  | Level 1 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
182 | User Story |  |  | Level 2 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
183 | User Story |  |  | Level 3 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
184 | User Story |  |  | Level 4 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
185 | User Story |  |  | Level 5 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
186 | User Story |  |  | Level 6 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
187 | User Story |  |  | Level 7 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
188 | User Story |  |  | Level 8 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
189 | User Story |  |  | Level 9 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
190 | User Story |  |  | Level 10 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
191 | User Story |  |  | Level 11 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
192 | User Story |  |  | Level 12 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
193 | User Story |  |  | Level 13 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
194 | User Story |  |  | Level 14 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
195 | User Story |  |  | Level 15 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
196 | User Story |  |  | Level 16 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
197 | User Story |  |  | Level 17 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
198 | User Story |  |  | Level 18 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
199 | User Story |  |  | Level 19 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
200 | User Story |  |  | Level 20 |  |  | lindamf | New |  | \game-design\story | \mvp | 3 | 1
201 | Epic | Art and design |  |  |  |  | lindamf | New | 35 | \assets | \mvp | 2
202 | Feature |  | UI/UX design |  |  |  |  | New | 3 | \game-design | \mvp | 2
203 | User Story |  |  | UX flow |  |  |  | New |  | \game-design | \mvp | 2 | 1
204 | Task |  |  |  | Identify interaction points |  |  | New |  | \game-design | \mvp | 2
205 | Task |  |  |  | Create tickets for each UI component |  |  | New |  | \game-design | \mvp | 2
206 | Task |  |  |  | Diagram user flow between points |  |  | New |  | \game-design | \mvp | 2
207 | User Story |  |  | Starting screen |  |  |  | New |  | \assets\graphics | \mvp | 2 | 1
208 | User Story |  |  | Level selection screen |  |  |  | New |  | \assets\graphics | \mvp | 2 | 1
209 | User Story |  |  | Profile screen |  |  |  | New |  | \assets\graphics | \mvp | 3 | 1
210 | User Story |  |  | Login dialog |  |  |  | New |  | \assets\graphics | \mvp | 3 | 1
211 | Feature |  | Level environmental design |  |  |  |  | New | 8 | \assets\graphics | \mvp | 3
212 | User Story |  |  | Level 1 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
213 | User Story |  |  | Level 2 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
214 | User Story |  |  | Level 3 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
215 | User Story |  |  | Level 4 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
216 | User Story |  |  | Level 5 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
217 | User Story |  |  | Level 6 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
218 | User Story |  |  | Level 7 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
219 | User Story |  |  | Level 8 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
220 | User Story |  |  | Level 9 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
221 | User Story |  |  | Level 10 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
222 | User Story |  |  | Level 11 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
223 | User Story |  |  | Level 12 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
224 | User Story |  |  | Level 13 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
225 | User Story |  |  | Level 14 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
226 | User Story |  |  | Level 15 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
227 | User Story |  |  | Level 16 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
228 | User Story |  |  | Level 17 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
229 | User Story |  |  | Level 18 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
230 | User Story |  |  | Level 19 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
231 | User Story |  |  | Level 20 |  |  |  | New |  | \assets\graphics | \mvp | 3 | 2
232 | Feature |  | Unit animation |  |  |  | Heather Fry | New | 13 | \assets\animations | \mvp | 2 |  | Draw the animation cells for each of the units. Each tower should have a repeating animation of 16 cells.
233 | User Story |  |  | Hero sprite sheet - General Clawdius Maximus |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Clawdius Maximus. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
234 | User Story |  |  | Hero sprite sheet - Sir Pounce-a-Lot |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Sir Pounce-a-Lot. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
235 | User Story |  |  | Hero sprite sheet - Meowdusa |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Meowdusa. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
236 | User Story |  |  | Hero sprite sheet - Purrlin the Mage |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Purrlin the Mage. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
237 | User Story |  |  | Hero sprite sheet - Graybeard the Gnawer |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Graybeard the Gnawer. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
238 | User Story |  |  | Hero sprite sheet - Fleablight |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Fleablight. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
239 | User Story |  |  | Hero sprite sheet - Stormtail |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Stormtail. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
240 | User Story |  |  | Hero sprite sheet - Chitterjaw |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Chitterjaw. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
241 | User Story |  |  | Hero sprite sheet - Rat King |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Rat King. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
242 | User Story |  |  | Sprite sheet - Basic Squeakers |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Basic Squeakers. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
243 | User Story |  |  | Sprite sheet - Flashpaws |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Flashpaws. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
244 | User Story |  |  | Sprite sheet - Mindwhiskers |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Mindwhiskers. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
245 | User Story |  |  | Sprite sheet - Titantails |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Titantails. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
246 | User Story |  |  | Sprite sheet - Voltfangs |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Voltfangs. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
247 | User Story |  |  | Sprite sheet - Shadowsnouts |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Shadowsnouts. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
248 | User Story |  |  | Sprite sheet - Gutrotters |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Gutrotters. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
249 | User Story |  |  | Sprite sheet - Bonecrunchers |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Bonecrunchers. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
250 | User Story |  |  | Sprite sheet - Shriekmaw |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Shriekmaw. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
251 | User Story |  |  | Sprite sheet - Cinderfur |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Cinderfur. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
252 | User Story |  |  | Sprite sheet - Frostfeet |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Frostfeet. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
253 | User Story |  |  | Sprite sheet - Fleabombs |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Fleabombs. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
254 | User Story |  |  | Sprite sheet - Chewtank |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for Chewtank. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
255 | User Story |  |  | Sprite sheet - Basic Claw Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Basic Claw Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
256 | User Story |  |  | Sprite sheet - Sticky Paws Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Sticky Paws Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
257 | User Story |  |  | Sprite sheet - Cat Nap Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Cat Nap Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
258 | User Story |  |  | Sprite sheet - Pied Piper Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Pied Piper Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
259 | User Story |  |  | Sprite sheet - Yarn Ball Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Yarn Ball Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
260 | User Story |  |  | Sprite sheet - Hero Towers |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Hero Towers. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
261 | User Story |  |  | Sprite sheet - Mouse Trap Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Mouse Trap Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
262 | User Story |  |  | Sprite sheet - Sticky Trap Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Sticky Trap Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
263 | User Story |  |  | Sprite sheet - Fish Bone Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Fish Bone Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
264 | User Story |  |  | Sprite sheet - Tuna Storm Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Tuna Storm Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
265 | User Story |  |  | Sprite sheet - Drenched Paw Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Drenched Paw Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
266 | User Story |  |  | Sprite sheet - Blazing Whisker Tower |  |  | Heather Fry | New |  | \assets\animations | \mvp | 2 | 1 | Draw the animation cells for the Blazing Whisker Tower. Each tower should have a repeating animation of 16 cells. | * Each cell needs to be 256x256 px * There are 16 cells that will animate consecutively * Follow the art style as decided on in #204
267 | Epic | Audio | [5 empty] | New | 21 | \assets | \mvp | 2
268 | Feature |  | Sound effects |  |  |  |  | New | 5 | \assets\sounds | \mvp | 2
269 | User Story |  |  | UI sound effects |  |  |  | New |  | \assets\sounds | \mvp | 2 | 1
270 | User Story |  |  | Level sound effects |  |  |  | New |  | \assets\sounds | \mvp | 3 | 2
271 | Task |  |  |  | Animals |  |  | New |  | \assets\sounds | \mvp | 3
272 | Task |  |  |  | Natural |  |  | New |  | \assets\sounds | \mvp | 3
273 | User Story |  |  | Unit sound effects |  |  |  | New |  | \assets\sounds | \mvp | 3 | 2
274 | Task |  |  |  | Sound effects - General Clawdius Maximus |  |  | New |  | \assets\sounds | \mvp | 3
275 | Task |  |  |  | Sound effects - Sir Pounce-a-Lot |  |  | New |  | \assets\sounds | \mvp | 3
276 | Task |  |  |  | Sound effects - Meowdusa |  |  | New |  | \assets\sounds | \mvp | 3
277 | Task |  |  |  | Sound effects - Purrlin the Mage |  |  | New |  | \assets\sounds | \mvp | 3
278 | Task |  |  |  | Sound effects - Graybeard the Gnawer |  |  | New |  | \assets\sounds | \mvp | 3
279 | Task |  |  |  | Sound effects - Fleablight |  |  | New |  | \assets\sounds | \mvp | 3
280 | Task |  |  |  | Sound effects - Stormtail |  |  | New |  | \assets\sounds | \mvp | 3
281 | Task |  |  |  | Sound effects - Chitterjaw |  |  | New |  | \assets\sounds | \mvp | 3
282 | Task |  |  |  | Sound effects - Rat King |  |  | New |  | \assets\sounds | \mvp | 3
283 | Task |  |  |  | Sound effects - Basic Squeakers |  |  | New |  | \assets\sounds | \mvp | 3
284 | Task |  |  |  | Sound effects - Flashpaws |  |  | New |  | \assets\sounds | \mvp | 3
285 | Task |  |  |  | Sound effects - Mindwhiskers |  |  | New |  | \assets\sounds | \mvp | 3
286 | Task |  |  |  | Sound effects - Titantails |  |  | New |  | \assets\sounds | \mvp | 3
287 | Task |  |  |  | Sound effects - Voltfangs |  |  | New |  | \assets\sounds | \mvp | 3
288 | Task |  |  |  | Sound effects - Shadowsnouts |  |  | New |  | \assets\sounds | \mvp | 3
289 | Task |  |  |  | Sound effects - Gutrotters |  |  | New |  | \assets\sounds | \mvp | 3
290 | Task |  |  |  | Sound effects - Bonecrunchers |  |  | New |  | \assets\sounds | \mvp | 3
291 | Task |  |  |  | Sound effects - Shriekmaw |  |  | New |  | \assets\sounds | \mvp | 3
292 | Task |  |  |  | Sound effects - Cinderfur |  |  | New |  | \assets\sounds | \mvp | 3
293 | Task |  |  |  | Sound effects - Frostfeet |  |  | New |  | \assets\sounds | \mvp | 3
294 | Task |  |  |  | Sound effects - Fleabombs |  |  | New |  | \assets\sounds | \mvp | 3
295 | Task |  |  |  | Sound effects - Chewtank |  |  | New |  | \assets\sounds | \mvp | 3
296 | Task |  |  |  | Sound effects - Basic Claw Tower |  |  | New |  | \assets\sounds | \mvp | 3
297 | Task |  |  |  | Sound effects - Sticky Paws Tower |  |  | New |  | \assets\sounds | \mvp | 3
298 | Task |  |  |  | Sound effects - Cat Nap Tower |  |  | New |  | \assets\sounds | \mvp | 3
299 | Task |  |  |  | Sound effects - Pied Piper Tower |  |  | New |  | \assets\sounds | \mvp | 3
300 | Task |  |  |  | Sound effects - Yarn Ball Tower |  |  | New |  | \assets\sounds | \mvp | 3
301 | Task |  |  |  | Sound effects - Hero Towers |  |  | New |  | \assets\sounds | \mvp | 3
302 | Task |  |  |  | Sound effects - Mouse Trap Tower |  |  | New |  | \assets\sounds | \mvp | 3
303 | Task |  |  |  | Sound effects - Sticky Trap Tower |  |  | New |  | \assets\sounds | \mvp | 3
304 | Task |  |  |  | Sound effects - Fish Bone Tower |  |  | New |  | \assets\sounds | \mvp | 3
305 | Task |  |  |  | Sound effects - Tuna Storm Tower |  |  | New |  | \assets\sounds | \mvp | 3
306 | Task |  |  |  | Sound effects - Drenched Paw Tower |  |  | New |  | \assets\sounds | \mvp | 3
307 | Task |  |  |  | Sound effects - Blazing Whisker Tower |  |  | New |  | \assets\sounds | \mvp | 3
308 | Feature |  | Background music |  |  |  | Heather Fry | New | 8 | \assets\music | \mvp | 2
309 | User Story |  |  | Main theme to play in UI |  |  | Heather Fry | New |  | \assets\music | \mvp | 2 | 2
310 | User Story |  |  | Music for levels |  |  | Heather Fry | New |  | \assets\music | \mvp | 3 | 2
311 | Task |  |  |  | Background music for level 1 |  | Heather Fry | New |  | \assets\music | \mvp | 3
312 | Task |  |  |  | Background music for level 2 |  | Heather Fry | New |  | \assets\music | \mvp | 3
313 | Task |  |  |  | Background music for level 3 |  | Heather Fry | New |  | \assets\music | \mvp | 3
314 | Task |  |  |  | Background music for level 4 |  | Heather Fry | New |  | \assets\music | \mvp | 3
315 | Task |  |  |  | Background music for level 5 |  | Heather Fry | New |  | \assets\music | \mvp | 3
316 | Task |  |  |  | Background music for level 6 |  | Heather Fry | New |  | \assets\music | \mvp | 3
317 | Task |  |  |  | Background music for level 7 |  | Heather Fry | New |  | \assets\music | \mvp | 3
318 | Task |  |  |  | Background music for level 8 |  | Heather Fry | New |  | \assets\music | \mvp | 3
319 | Task |  |  |  | Background music for level 9 |  | Heather Fry | New |  | \assets\music | \mvp | 3
320 | Task |  |  |  | Background music for level 10 |  | Heather Fry | New |  | \assets\music | \mvp | 3
321 | Task |  |  |  | Background music for level 11 |  | Heather Fry | New |  | \assets\music | \mvp | 3
322 | Task |  |  |  | Background music for level 12 |  | Heather Fry | New |  | \assets\music | \mvp | 3
323 | Task |  |  |  | Background music for level 13 |  | Heather Fry | New |  | \assets\music | \mvp | 3
324 | Task |  |  |  | Background music for level 14 |  | Heather Fry | New |  | \assets\music | \mvp | 3
325 | Task |  |  |  | Background music for level 15 |  | Heather Fry | New |  | \assets\music | \mvp | 3
326 | Task |  |  |  | Background music for level 16 |  | Heather Fry | New |  | \assets\music | \mvp | 3
327 | Task |  |  |  | Background music for level 17 |  | Heather Fry | New |  | \assets\music | \mvp | 3
328 | Task |  |  |  | Background music for level 18 |  | Heather Fry | New |  | \assets\music | \mvp | 3
329 | Task |  |  |  | Background music for level 19 |  | Heather Fry | New |  | \assets\music | \mvp | 3
330 | Task |  |  |  | Background music for level 20 |  | Heather Fry | New |  | \assets\music | \mvp | 3
331 | User Story |  |  | Music for cutscenes |  |  | Heather Fry | New |  | \assets\music | \mvp | 3 | 2
332 | Task |  |  |  | Musical score for introduction |  | Heather Fry | New |  | \assets\music | \mvp | 3
333 | Task |  |  |  | Musical score for level 1 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
334 | Task |  |  |  | Musical score for level 2 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
335 | Task |  |  |  | Musical score for level 3 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
336 | Task |  |  |  | Musical score for level 4 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
337 | Task |  |  |  | Musical score for level 5 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
338 | Task |  |  |  | Musical score for level 6 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
339 | Task |  |  |  | Musical score for level 7 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
340 | Task |  |  |  | Musical score for level 8 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
341 | Task |  |  |  | Musical score for level 9 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
342 | Task |  |  |  | Musical score for level 10 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
343 | Task |  |  |  | Musical score for level 11 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
344 | Task |  |  |  | Musical score for level 12 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
345 | Task |  |  |  | Musical score for level 13 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
346 | Task |  |  |  | Musical score for level 14 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
347 | Task |  |  |  | Musical score for level 15 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
348 | Task |  |  |  | Musical score for level 16 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
349 | Task |  |  |  | Musical score for level 17 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
350 | Task |  |  |  | Musical score for level 18 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
351 | Task |  |  |  | Musical score for level 19 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
352 | Task |  |  |  | Musical score for level 20 cutscene |  | Heather Fry | New |  | \assets\music | \mvp | 3
353 | Feature |  | Voiceovers |  |  |  |  | New | 5 | \assets\voices | \mvp | 4
354 | User Story |  |  | Voiceovers for cutscenes |  |  |  | New |  | \assets\voices | \mvp | 4 | 3
355 | Task |  |  |  | Voiceoves for introduction |  |  | New |  | \assets\voices | \mvp | 4
356 | Task |  |  |  | Voiceoves for level 1 cutscene |  |  | New |  | \assets\voices | \mvp | 4
357 | Task |  |  |  | Voiceoves for level 2 cutscene |  |  | New |  | \assets\voices | \mvp | 4
358 | Task |  |  |  | Voiceoves for level 3 cutscene |  |  | New |  | \assets\voices | \mvp | 4
359 | Task |  |  |  | Voiceoves for level 4 cutscene |  |  | New |  | \assets\voices | \mvp | 4
360 | Task |  |  |  | Voiceoves for level 5 cutscene |  |  | New |  | \assets\voices | \mvp | 4
361 | Task |  |  |  | Voiceoves for level 6 cutscene |  |  | New |  | \assets\voices | \mvp | 4
362 | Task |  |  |  | Voiceoves for level 7 cutscene |  |  | New |  | \assets\voices | \mvp | 4
363 | Task |  |  |  | Voiceoves for level 8 cutscene |  |  | New |  | \assets\voices | \mvp | 4
364 | Task |  |  |  | Voiceoves for level 9 cutscene |  |  | New |  | \assets\voices | \mvp | 4
365 | Task |  |  |  | Voiceoves for level 10 cutscene |  |  | New |  | \assets\voices | \mvp | 4
366 | Task |  |  |  | Voiceoves for level 11 cutscene |  |  | New |  | \assets\voices | \mvp | 4
367 | Task |  |  |  | Voiceoves for level 12 cutscene |  |  | New |  | \assets\voices | \mvp | 4
368 | Task |  |  |  | Voiceoves for level 13 cutscene |  |  | New |  | \assets\voices | \mvp | 4
369 | Task |  |  |  | Voiceoves for level 14 cutscene |  |  | New |  | \assets\voices | \mvp | 4
370 | Task |  |  |  | Voiceoves for level 15 cutscene |  |  | New |  | \assets\voices | \mvp | 4
371 | Task |  |  |  | Voiceoves for level 16 cutscene |  |  | New |  | \assets\voices | \mvp | 4
372 | Task |  |  |  | Voiceoves for level 17 cutscene |  |  | New |  | \assets\voices | \mvp | 4
373 | Task |  |  |  | Voiceoves for level 18 cutscene |  |  | New |  | \assets\voices | \mvp | 4
374 | Task |  |  |  | Voiceoves for level 19 cutscene |  |  | New |  | \assets\voices | \mvp | 4
375 | Task |  |  |  | Voiceoves for level 20 cutscene |  |  | New |  | \assets\voices | \mvp | 4
376 | Epic | Programming |  |  |  |  | Edward Fry | New | 21 | \code | \mvp | 3
377 | Feature |  | Training |  |  |  | Edward Fry | New | 5 | \code | \mvp | 3
378 | Research |  |  | Technical game design training |  |  | Elizabeth Fry | New | 2 | \code | \mvp | 3
379 | Research |  |  | Godot training |  |  | Elizabeth Fry | New | 2 | \code | \mvp | 3
380 | Feature |  | Technical design |  |  |  | Edward Fry | New | 5 | \code | \mvp | 1
381 | User Story |  |  | Non-functional requirements |  |  | Edward Fry | New |  | \code | \mvp | 2 | 1
382 | Task |  |  |  | Performance |  | Edward Fry | New |  | \code | \mvp | 2
383 | Task |  |  |  | Security |  | Edward Fry | New |  | \code | \mvp | 2
384 | Task |  |  |  | Scalability |  | Edward Fry | New |  | \code | \mvp | 2
385 | Task |  |  |  | Availability |  | Edward Fry | New |  | \code | \mvp | 2
386 | Task |  |  |  | Reliability |  | Edward Fry | New |  | \code | \mvp | 2
387 | Task |  |  |  | Maintainability |  | Edward Fry | New |  | \code | \mvp | 2
388 | User Story |  |  | Backend |  |  | Edward Fry | New |  | \code\back-end | \mvp | 1 | 1
389 | User Story |  |  | Database |  |  | Edward Fry | New |  | \code\back-end | \mvp | 1 | 1
390 | User Story |  |  | Frontend |  |  | Edward Fry | New |  | \code\front-end | \mvp | 1 | 1
391 | User Story |  |  | Communication |  |  | Edward Fry | New |  | \code\back-end | \mvp | 1 | 1
392 | User Story |  |  | Integration with game engine |  |  | Edward Fry | New |  | \code\front-end | \mvp | 1 | 1
393 | Feature |  | Implementation |  |  |  |  | New |  | \code | \mvp | 2
394 | Feature |  | Level design tool |  |  |  |  | New |  | \code | \mvp | 4
395 | User Story |  |  | Technical design |  |  |  | New |  | \code | \mvp | 4
396 | User Story |  |  | Implementation |  |  |  | New |  | \code\front-end | \mvp | 4
397 | User Story |  |  | Testing |  |  |  | New |  | \code | \mvp | 4 | 2
398 | Epic | Level design | [5 empty] | New | 13 | \game-design\levels | \mvp | 2
399 | Feature |  | Level layout and scripting |  |  |  |  | New | 8 | \game-design\levels | \mvp | 2
400 | User Story |  |  | Level 1 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
401 | User Story |  |  | Level 2 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
402 | User Story |  |  | Level 3 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
403 | User Story |  |  | Level 4 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
404 | User Story |  |  | Level 5 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
405 | User Story |  |  | Level 6 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
406 | User Story |  |  | Level 7 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
407 | User Story |  |  | Level 8 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
408 | User Story |  |  | Level 9 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
409 | User Story |  |  | Level 10 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
410 | User Story |  |  | Level 11 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
411 | User Story |  |  | Level 12 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
412 | User Story |  |  | Level 13 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
413 | User Story |  |  | Level 14 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
414 | User Story |  |  | Level 15 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
415 | User Story |  |  | Level 16 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
416 | User Story |  |  | Level 17 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
417 | User Story |  |  | Level 18 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
418 | User Story |  |  | Level 19 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
419 | User Story |  |  | Level 20 |  |  |  | New |  | \game-design\levels | \mvp | 2 | 2
420 | Feature |  | Balancing and pacing iteration |  |  |  |  | New | 8 | \game-design\levels | \mvp | 2
421 | Epic | DevOps |  |  |  |  | Edward Fry | New | 8 | \admin\devops | \mvp | 2
422 | Feature |  | Integration pipeline setup |  |  |  | Edward Fry | New | 5 | \admin\devops | \mvp | 2
423 | Feature |  | Environment setup |  |  |  | Edward Fry | New | 3 | \admin\it | \mvp | 2
424 | Feature |  | Deployment pipeline setup |  |  |  | Edward Fry | New | 3 | \admin\devops | \mvp | 2
449 | Epic | Testing |  |  |  |  | antastic@live.com | New | 35 | \qa | \mvp | 2
450 | Feature |  | Training |  |  |  | antastic@live.com | New | 8 | \qa | \mvp | 3
451 | Research |  |  | Basic testing concepts |  |  | antastic@live.com | New | 3 | \qa | \mvp | 3
452 | Research |  |  | Test plans in Azure Devops |  |  | antastic@live.com | New | 2 | \qa | \mvp | 3
453 | Research |  |  | Automated testing |  |  | antastic@live.com | New | 3 | \qa\automated | \mvp | 2
454 | Feature |  | Internal Testing |  |  |  | antastic@live.com | New |  | \qa | \mvp | 2
455 | User Story |  |  | Write test cases |  |  | antastic@live.com | New |  | \qa\manual | \mvp | 3
456 | User Story |  |  | Construct automated tests |  |  | antastic@live.com | New |  | \qa\automated | \mvp | 3
457 | User Story |  |  | Run automated tests |  |  | antastic@live.com | New |  | \qa\automated | \mvp | 2
458 | User Story |  |  | Execute manual tests |  |  | antastic@live.com | New |  | \qa\manual | \mvp | 2
425 | User Story |  |  | Fix bugs |  |  | Elizabeth Fry | New |  | \code | \mvp | 3
426 | Feature |  | External Testing |  |  |  |  | New |  | \qa | \mvp | 3
427 | User Story |  |  | Alpha testing |  |  |  | New |  | \qa | \mvp | 4
428 | User Story |  |  | Beta testing |  |  |  | New |  | \qa | \mvp | 3
429 | Research |  |  | Player feedback collection |  |  |  | New |  | \marketing | \mvp | 3
430 | Epic | Launch | [5 empty] | New | 5 | \marketing | \mvp | 3
431 | Feature |  | Marketing & Promotion |  |  |  |  | New |  | \marketing | \mvp | 3
432 | User Story |  |  | Trailers creation |  |  |  | New |  | \assets\animations | \mvp | 3 | 2
433 | User Story |  |  | Social media |  |  |  | New |  | \marketing\social | \mvp | 3 | 1
434 | User Story |  |  | Press kits |  |  |  | New |  | \marketing\advertising | \mvp | 3 | 1
435 | User Story |  |  | Influencer outreach |  |  |  | New |  | \marketing | \mvp | 4 | 1
436 | Feature |  | Distribution |  |  |  |  | New |  | \marketing\storefronts | \mvp | 4
437 | Feature |  | Platform submission |  |  |  | Edward Fry | New | 2 | \admin\devops | \mvp | 2
438 | User Story |  |  | Steam |  |  | Edward Fry | New |  | \admin\devops | \mvp | 2 | 1
439 | User Story |  |  | Mobile |  |  |  | New |  | \admin\devops | \mvp | 3 | 2
440 | User Story |  |  | Consoles |  |  |  | New |  | \admin\devops | \mvp | 4 | 2
441 | Feature |  | Day-one patch and support |  |  |  |  | New |  | \marketing | \mvp | 3
442 | Epic | Post-Launch | [5 empty] | New | 8 | \marketing | \mvp | 2
443 | Feature |  | Support & updates |  |  |  |  | New |  | \qa | \mvp | 2
444 | User Story |  |  | Bug fixes and patches |  |  |  | New |  | \code | \mvp | 3
445 | User Story |  |  | Content dates and DLC |  |  |  | New |  | \marketing | \mvp | 3
446 | Feature |  | Community Engagement |  |  |  |  | New |  | \marketing | \mvp | 3
447 | User Story |  |  | Forums and social media |  |  |  | New |  | \marketing\social | \mvp | 3
448 | User Story |  |  | Feedback loops for future improvements |  |  |  | New |  | \marketing | \mvp | 3

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Active | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Active | 1 | Select User... | Closed | 1 | Select User... | Active | 1 | Bug | Select User... | Active | 1 | Bug | New | Active | Active
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_M/d/yyyy h:mm AM/PM | readOnlyTestRange_General | \admin | \mvp | antastic@live.com | Closed | 2 | antastic@live.com | Approved | 2 | antastic@live.com | Closed | 2 | antastic@live.com | Approved | 2 | antastic@live.com | Closed | antastic@live.com | Closed | 2 | antastic@live.com | Blocked | 2 | antastic@live.com | Blocked | 2 | antastic@live.com | Blocked | 2 | antastic@live.com | Design | 2 | antastic@live.com | Approved | 2 | Epic | antastic@live.com | Approved | 2 | Code Review Request | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_9D-7E-48-98-DA-83-23-5A-24-A0-F6-29-1B-B0-9C-EE-1C-7F-84-40-AE-B1-8F-43-57-DC-49-FB-D0-51-AD-0B | Blocked | Approved
|  |  |  | \admin\accounting | \mvp\2025-sprint1 | Edward Fry | New | 3 | Edward Fry | Blocked | 3 | Edward Fry | New | 3 | Edward Fry | Blocked | 3 | Edward Fry | New | Edward Fry | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Issue_System.State | 3 | Edward Fry | Closed | 3 | Edward Fry | Closed | 3 | Edward Fry | Done | 3 | Edward Fry | Ready | 3 | Edward Fry | Blocked | 3 | Feature | Edward Fry | Blocked | 3 | Code Review Response |  | Done | Blocked
|  |  |  | \admin\devops | \mvp\2025-sprint2 | Elizabeth Fry | Removed | 4 | Elizabeth Fry | Closed | 4 | Elizabeth Fry | Removed | 4 | Elizabeth Fry | Closed | 4 | Elizabeth Fry | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Impediment_System.State | Elizabeth Fry |  | 4 | Elizabeth Fry | New | 4 | Elizabeth Fry | New | 4 | Elizabeth Fry | New | 4 | Elizabeth Fry | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Test Case_System.State | 4 | Elizabeth Fry | Closed | 4 | Impediment | Elizabeth Fry | Closed | 4 | Epic |  | New | Closed
|  |  |  | \admin\it | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_System.IterationPath | Heather Fry | Resolved | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_BB-70-B8-41-88-31-3F-7F-BA-44-98-0C-91-E6-96-79-8B-C5-61-63-B8-FB-5A-51-9C-8A-B5-29-A7-9F-82-25 | Heather Fry | Done | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Bug_Microsoft.VSTS.Common.Priority | Heather Fry | Resolved | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Epic_Microsoft.VSTS.Common.Priority | Heather Fry | Done | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Feature_Microsoft.VSTS.Common.Priority | Heather Fry |  | Heather Fry |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Issue_Microsoft.VSTS.Common.Priority | Heather Fry | On hold | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Research_Microsoft.VSTS.Common.Priority | Heather Fry | On hold | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Spike_Microsoft.VSTS.Common.Priority | Heather Fry | Removed | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Task_Microsoft.VSTS.Common.Priority | Heather Fry |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Test Case_Microsoft.VSTS.Common.Priority | Heather Fry | Done | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_User Story_Microsoft.VSTS.Common.Priority | Issue | Heather Fry | Done | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Microsoft.VSTS.Common.Priority | Feature |  | Removed | Done
|  |  |  | \admin\project-management |  | lindamf | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_00-68-8F-7F-EC-58-AF-73-00-E5-4B-59-14-14-D4-BF-A8-78-F8-6D-6C-BF-0C-DC-0F-C4-35-D2-EE-01-0E-15 |  | lindamf | Failed |  | lindamf | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Epic_System.State |  | lindamf | New |  | lindamf |  | lindamf |  |  | lindamf | Review |  | lindamf | Review |  | lindamf | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Task_System.State |  | lindamf |  |  | lindamf | Failed |  | Research | lindamf | Failed |  | Feedback Request |  | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_7C-BC-9D-AD-C6-01-74-3E-BB-9E-61-77-34-9E-C8-EF-76-BF-67-D8-C9-21-23-84-F0-1F-CB-A3-EC-D2-AA-4B | New
|  |  |  | \assets |  | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_F4-B1-81-B9-31-7F-EB-31-5A-B1-F5-99-12-E0-C2-C6-74-82-01-62-4A-8D-F1-4C-2E-E2-E8-66-6B-07-6A-DB |  |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Bug_System.AssignedTo | New |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Epic_System.AssignedTo |  |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Feature_System.AssignedTo | On hold |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Impediment_System.AssignedTo |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Issue_System.AssignedTo |  |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Research_System.AssignedTo | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Research_System.State |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Spike_System.AssignedTo | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Spike_System.State |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Task_System.AssignedTo |  |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Test Case_System.AssignedTo |  |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_User Story_System.AssignedTo | New |  | Spike | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_System.AssignedTo | New |  | Feedback Response |  |  | On hold
|  |  |  | \assets\animations | [5 empty] | On hold | [5 empty] | Removed | [19 empty] | On hold |  | Task |  | On hold |  | Impediment |  |  | Removed
|  |  |  | \assets\graphics | [5 empty] | Passed | [5 empty] | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Feature_System.State | [19 empty] | Passed |  | Test Case |  | Passed |  | Issue |  |  | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_73-E4-60-8A-28-C6-AE-01-F1-59-05-9F-65-87-00-C6-19-12-E6-4C-A1-29-99-3C-E7-EB-2F-59-66-B9-D1-87
|  |  |  | \assets\music | [5 empty] | Removed | [25 empty] | Removed |  | User Story |  | Removed |  | Research
|  |  |  | \assets\sounds | [5 empty] | Testing | [25 empty] | Testing |  | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_System.WorkItemType |  | Testing |  | Shared Parameter
|  |  |  | \assets\voices | [5 empty] | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_Bug_System.State | [25 empty] | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_User Story_System.State |  |  |  | Resolved |  | Shared Steps
|  |  |  | \code | [35 empty] | Review |  | Spike
|  |  |  | \code\back-end | [35 empty] | Design |  | Task
|  |  |  | \code\front-end | [35 empty] | Ready |  | Test Case
|  |  |  | \code\install | [35 empty] | all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_System.State |  | Test Plan
|  |  |  | \database | [37 empty] | Test Suite
|  |  |  | \database\admin | [37 empty] | User Story
|  |  |  | \database\data | [37 empty] | VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_A7-A2-20-8A-34-7F-72-2A-71-68-81-E0-59-38-21-49-5E-0A-5A-9C-E6-C7-97-90-30-24-DC-53-DC-47-82-6F
\database\programming
\game-design
\game-design\levels
\game-design\rules
\game-design\story
\marketing
\marketing\advertising
\marketing\social
\marketing\storefronts
\qa
\qa\automated
\qa\manual
all_VSTS_cec4a20d_e9e3_4733_8ab5_68cfadae7905_System.AreaPath